## DSI 1on1 Tracker
Item / Action | Report | Type | Owner | Due | Status | Priority | Raised | Notes
Ship AlertPriority v4 risk-summary output to FCC review | Priya | Action | Priya | 2026-07-14 | In progress | High | 2026-06-24 | Fold in compliance feedback on routing labels
Payer-extraction accuracy below threshold on scanned EOBs | Raj | Blocker | Raj | 2026-07-07 | Blocked | High | 2026-06-30 | Low-DPI faxes; test doc-classification pre-filter
Choose vector DB for AML case-notes RAG POC | Omar | Decision | Engin | 2026-07-16 | Not started | Medium | 2026-06-30 | Managed vs on-prem; align with InfoSec
Strong DSI Development Associates ML-ops session | Elena | Feedback | Engin |  | Done | Low | 2026-06-17 | Clear pacing; consider recording for reuse
Map GPP/PME/PRT payment lifecycle with PST team | Dan | Action | Dan | 2026-07-11 | In progress | Medium | 2026-06-17 | Schedule interview; capture ACH handoffs
Explore path to Senior Data Scientist promotion | Priya | Career/Growth | Priya | 2026-08-01 | Not started | Medium | 2026-06-24 | Identify a lead-level project; FCC visibility
Rebuild application-catalog page on DSI SharePoint | Maria | Action | Maria | 2026-07-18 | Not started | Low | 2026-06-30 | Reuse taxonomy; link to project portfolio
Decide whether to sunset legacy XGBoost dashboard | Surya | Decision | Engin | 2026-07-09 | In progress | Medium | 2026-06-24 | Migrate to Streamlit; check downstream users
Copilot Studio agent hallucinating on payer FAQ | Raj | Blocker | Raj | 2026-07-04 | Blocked | High | 2026-06-30 | Grounding data stale; refresh KB
Draft ODSC East 2027 talk abstract | Omar | Topic | Omar | 2026-07-22 | Not started | Low | 2026-06-24 | Multi-agent AML triage angle
Recognize initiative on SharePoint knowledge hub | Maria | Feedback | Engin |  | Done | Low | 2026-06-17 | Took ownership unprompted; keep momentum
Build validation harness for doc-classification model | Elena | Action | Elena | 2026-07-15 | In progress | High | 2026-06-24 | Precision/recall per doc type; add drift checks
Unclear priorities between AML and EOB tracks | Priya | Topic | Engin | 2026-07-05 | In progress | High | 2026-06-30 | Clarify quarterly focus; protect deep-work time
Pair on LangGraph agent build for mentorship | Dan | Career/Growth | Dan | 2026-07-25 | Not started | Medium | 2026-06-30 | Tie to fall-internship onboarding
Approve budget for CCA-F practice-exam resources | Omar | Decision | Engin | 2026-07-08 | Not started | Low | 2026-06-24 | Skilljar + third-party practice set
Consolidate HCA payment-flow interview notes | Dan | Action | Dan | 2026-07-12 | Done | Medium | 2026-06-03 | Merged into master lifecycle doc
Tighten model-monitoring report visuals | Surya | Feedback | Engin |  | Done | Low | 2026-06-17 | QuickSight cluttered; cut to top 3 metrics
Token-cost spike in unit-price extraction agent | Elena | Blocker | Elena | 2026-07-06 | In progress | Medium | 2026-06-30 | Prompt bloat; add token tracking + caching
Plan Q3 DSI training curriculum topics | Maria | Topic | Engin | 2026-07-20 | Not started | Medium | 2026-06-24 | Survey associates; add agentic-systems module
Interest in moving from IC to management track | Priya | Career/Growth | Priya | 2026-08-05 | Not started | Low | 2026-06-24 | Discuss what a first lead role would look like